## Product Backlog
Project Name | School Management And Reporting Tool (SMART)
Product Name: | SMART | [6 empty] | Complete Fields in Green!!!
Team ID: | 1001825785
| Team Member Name | [5 empty] | Initials | Student ID
Required | Shoaib Rain | [5 empty] | SR | 1001825785
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 26 |  |  |  | Total | Total number of features (in column H)
1 | 21 | 5 |  |  | 1 | Total features left at the end of Sprint #1
2 | 16 | 5 |  |  | 2 | Total features left at the end of Sprint #2
3 | 10 | 6 |  |  | 3 | ...and so on
4 | 6 | 4
5 | 2 | 4
6 | -2 | 4
©2016-2021 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License. | [6 empty] | Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a(n)… | I want to... | So that I can… | Notes
PERSON | 1 | 1 |  | 13 |  | Finished in Sprint 1 | Administrator | Track people’s names and email addresses | Find and contact them | Need a Person base class with to_string / operator<< name and a full_info method
STUDENT | 2 | 1 |  | 8 |  | Finished in Sprint 1 | Administrator | Track students by grade | Verify students’ progress | Need a Student derived class that includes the grade level (1-12)
PARENT | 3 | 1 |  | 3 |  | Finished in Sprint 1 | Administrator | Track parents | Coordinate on student progress | Need a Parent derived class
RELATE | 4 | 1 |  | 5 |  | Finished in Sprint 1 | Administrator | Associate each student with parents bidirectionally | Know which parents to contact | Mutual aggregate relationship
CLI | 5 | 1 | 25 | 13 |  | Finished in Sprint 1 | Administrator | Basic command line user interface | Verify the system before moving to a GUI | This is cli.cpp for sprint 1 only (optional for bonus points)
WINDOW | 6 | 2 |  | 13 |  | Finished in Sprint 2 | All | Use a windowed rather than command line interface | Use SMART more intuitively | Create a main window with a menu bar, data area, and status bar
D_STUDENT | 7 | 2 |  | 8 |  | Finished in Sprint 2 | Administrator | Create students via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
DISPLAY | 8 | 2 |  | 5 |  | Finished in Sprint 2 | Teacher | See all current data in the main window | Keep up with students | Display full_info for students and parents in a table in the data area
D_PARENT | 9 | 2 |  | 5 |  | Finished in Sprint 2 | Administrator | Create parents via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
D_RELATE | 10 | 2 |  | 8 |  | Finished in Sprint 2 | Administrator | Relate students to parents via dialogs | Conveniently enter the data | Dialog listing students and entering index, then same for parents
NEW | 11 | 2 |  | 2 |  | Finished in Sprint 2 | Administrator | Clear all data | Start a new school | Simply clear all elements from the vectors
SAVE | 12 | 3 |  | 13 |  | Finished in Sprint 3 | All | Write the data to persistent storage | Don’t have to re-enter data | See Lecture 15 for an object-oriented strategy to create the file format
LOAD | 13 | 3 |  | 8 |  | Finished in Sprint 3 | All | Load data for a school from persistent storage | Don’t have to re-enter data | Select file via a file chooser dialog
SAVEAS | 14 | 3 |  | 8 |  | Finished in Sprint 3 | Administrator | Save data to a different filename | Create backups or baselines for new schools | Select filename via a file chooser dialog
TOOLBAR | 15 | 3 |  | 5 |  | Finished in Sprint 3 | All | Use the major features via a toolbar | Point and click | Suggest using the Nim game’s toolbar as a baseline
ABOUT | 16 | 3 |  | 1 |  | Finished in Sprint 3 | Administrator | Display an About dialog with creator and version | Quickly determine which version is installed | Use Gtk::AboutDialog
AGG_IO | 17 | 3 | 25 | 21 |  | Finished in Sprint 3 | Administrator | Also save the aggregate data | Relationships are not lost | This is obviously critical in a real application
SUBJECT | 18 | 4 |  | 5 |  | Finished in Sprint 4 | Administrator | Select from a list of subjects offered | Defined courses for the students to take | These can be hard-coded – you may select the courses you offer (minimum 5)
COURSE | 19 | 4 |  | 13 |  | Finished in Sprint 4 | Administrator | Specify the courses to be offered to students | Give the students the needed knowledge | You may still use EntryDialog for these if you don’t have time for unified dialogs
SEMESTER | 20 | 4 |  | 5 |  | Finished in Sprint 4 | Administrator | Specify the semester and year | Define when courses are offered | fall, spring and summer are sufficient here
SECTION | 21 | 4 |  | 13 |  | Finished in Sprint 4 | Administrator | Define specific sections of each course | Students (and eventually teachers) unite
CBC | 22 | 4 |  | 13 |  |  | Administrator | Use a single dialog for related parents and students | Enter data more efficiently | Derive a self-populating template from Gtk::ComboBoxText – see requirements
TEACHER | 23 | 5 |  | 8 |  |  | Teacher | Track the subject mastery and sections taught | Know who’s teaching what each semester | This is the third class derived from Person
GRADE | 24 | 5 |  | 3 |  |  | Student | Define the grading system | Quantify academic progress | This is another enum class, with the same supporting functions
TRANSCRIPT | 25 | 5 |  | 8 |  |  | Student | Link student to classes with a grade | Track schedule and balance assignments | This is a Transcript association class that references a Student and Section with a Grade attribute (X means in progress). Store in a Mainwin::transcripts vector.
ITERATORS | 26 | 5 |  | 8 |  |  |  | TBD
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
UNIFIED |  |  | 36 | 13 |  |  | All | Replace all remaining dialog sequences with unified dialogs each | Enter data more quickly | This covers the 6 main dialogs – 5 data types plus the association class (student to section). Each unified dialog earns 6 points.
EDIT |  |  | 36 | 13 |  |  | Administrator | Permit editing the 5 major data types – students, parents, teachers, courses, and sections | Correct errors and changing personal info | Prerequisite: UNIFIED for an editable dialog. The same dialog that created the data can be used to edit it – just set the current values as defaults. An additional 6 points per dialog is awarded for editing the data. Consider an Edit menu.
SCROLL |  |  | 10 | 5 |  |  | All | Make the main window’s data area scrollable | See large volumes of data | This is easier than it sounds. The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
STATUS++ |  |  | 15 | 8 |  |  | All | Replace the Gtk::Label for the status bar with Gtk::Statusbar, and maintain a message stack | Better track status of messages | Just swapping Gtk::Statusbar for Gtk::Label is trivial. Think through how to manage a first-in last-out stack of messages
MULTI |  |  | 70 | 34 |  |  | Administrator | Permit multiple schools to be open simultaneously | Support work at the district level or above | As shown at the end of the Sprint 1 requirements, move the data management to a School class, with methods for Mainwin to handle a school. Mainwin then stores a vector of pointers to the open Schools, with one “active” at any given time (usually selected by a Window menu, but tabs also work well). This is similar to how Microsoft Office handles multiple open documents.
PHOTO |  |  | 40 | 21 |  |  | Teacher | Include photos of students | Learn students names more quickly | The photos can be stored as JPEG files in the program directory (since we have no database), so store the filename as a Student attribute and use a Gtk::Image to display it.
GPA |  |  | 15 | 8 |  |  | Student | List all classes with grades and a cumulative GPA | Enable students and their parents to track academic progress | List all of the classes ever attended by a selected student, the grade earned for each. Calculate and present a cumulative GPA (average of 4 points for an A, 3 for B, 2 for C, 1 for D, and 0 for F – omit I and X grades).

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2021-03-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Note: Due to the late project start, the results of this sprint will be provided to you (although you may use your own solution if you prefer)
Task ID | Feature ID | Assigned To | Task | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2021-03-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2021-04-06 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-12
Demo on | 2021-04-13
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-04-06 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-13
Demo on | 2021-04-13
| Remaining | Completed (this day)
Total Tasks | 7
Day 1 Left | 6 | 1
Day 2 Left | 5 | 1
Day 3 Left | 4 | 1
Day 4 Left | 3 | 1
Day 5 Left | 3 | 0
Day 6 Left | 0 | 3
Day 7 Left | -2 | 2
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SEMESTER |  | Write Semester enum | Completed Day 2
2 |  |  | Implement operator<< | Completed Day 2
3 |  |  | Implement load_semester | Completed Day 2
4
5 | SUBJECT |  | Write Subject enum | Completed Day 3
6 |  |  | Implement operator<< | Completed Day 3
7 |  |  | Implement load_subject | Completed Day 3
8 |  |  | Write subjects_vector (for iteration) | Completed Day 3
9
10 | COURSE |  | Write Course class | Completed Day 4
11 |  |  | Implement operator<< | Completed Day 4
12 |  |  | Implement Course::save | Completed Day 4
13 |  |  | Implement Course::Course(ist) | Completed Day 4
14
15 | SECTION |  | Write Section class | Completed Day 4
16 |  |  | Implement operator<< | Completed Day 4
17 |  |  | Implement Section::save | Completed Day 4
18 |  |  | Implement Section::Course(ist) | Completed Day 4
19
20 |  |  | Mainwin: Add Insert > Course and Section | Completed Day 5
21 |  |  | Find new toolbar buttons and credit in Help > About | Completed Day 5
22 |  |  | Mainwin: Add toolbar buttons for Course and Section | Completed Day 5
23
24 |  |  | Mainwin: Add View > Students, Parents, Courses, Sections | Completed Day 5
25 |  |  | Add View enum and View parameter to show_data | Completed Day 5
26 |  |  | Add static current_view to show_data to remember view | Completed Day 5
27 |  |  | Update show_data to show different data types | Completed Day 5
28
29 |  |  | Write Mainwin::on_new_course_click using EntryDialog | Completed Day 6
30 |  |  | Write Mainwin::on_new_section_click using EntryDialog | Completed Day 6
31
32 |  |  | Mainwin: Update on_save_click to save courses and sections | Completed Day 7
33 |  |  | Mainwin: Update on_open_click to load courses and sections | Completed Day 7
34 |  |  | Mainwin: Add logic to load v0.1 files (pre-courses/sections) | Completed Day 7
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2021-04-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84