## Product Backlog
Project Name | School Management And Reporting Tool (SMART)
Product Name: | SMART SCHOOL MANAGEMENT SYSTEM | [6 empty] | Complete Fields in Green!!!
Team ID: | Shoaib Rain 1001825785
| Team Member Name | [5 empty] | Initials | Student ID
Required | Shoaib Rain | [5 empty] | SR | 1001825785
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 27 |  |  |  | Total | Total number of features (in column H)
1 | 22 | 5 |  |  | 1 | Total features left at the end of Sprint #1
2 | 16 | 6 |  |  | 2 | Total features left at the end of Sprint #2
3 | 11 | 5 |  |  | 3 | Total features left at the end of sprint#3
4 | 6 | 0
5 | 6 | 0
6 | 6 | 0
This work is licensed under a Creative Commons Attribution 4.0 International License. | [6 empty] | Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a(n)… | I want to... | So that I can… | Notes
PERSON | 1 | 1 |  | 13 | 1 | Finished in Sprint 1 | Administrator | Track people’s names and email addresses | Find and contact them | Need a Person base class with to_string / operator<< name and a full_info method
STUDENT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Administrator | Track students by grade | Verify students’ progress | Need a Student derived class that includes the grade level (1-12)
PARENT | 3 | 1 |  | 3 | 1 | Finished in Sprint 1 | Administrator | Track parents | Coordinate on student progress | Need a Parent derived class
RELATE | 4 | 1 |  | 5 | 1 | Finished in Sprint 1 | Administrator | Associate each student with parents bidirectionally | Know which parents to contact | Mutual aggregate relationship
CLI | 5 | 1 | 25 | 13 | 1 | Finished in Sprint 1 | Administrator | Basic command line user interface | Verify the system before moving to a GUI | This is cli.cpp for sprint 1 only (optional for bonus points)
WINDOW | 6 | 2 |  | 13 | 2 | Finished in Sprint 2 | All | Use a windowed rather than command line interface | Use SMART more intuitively | Create a main window with a menu bar, data area, and status bar
D_STUDENT | 7 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Create students via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
DISPLAY | 8 | 2 |  | 5 | 2 | Finished in Sprint 2 | Teacher | See all current data in the main window | Keep up with students | Display full_info for students and parents in a table in the data area
D_PARENT | 9 | 2 |  | 5 | 2 | Finished in Sprint 2 | Administrator | Create parents via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
D_RELATE | 10 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Relate students to parents via dialogs | Conveniently enter the data | Dialog listing students and entering index, then same for parents
NEW | 11 | 2 |  | 2 | 2 | Finished in Sprint 2 | Administrator | Clear all data | Start a new school | Simply clear all elements from the vectors
SAVE | 12 | 3 |  | 13 | 3 | Finished in Sprint 3 | All | Write the data to persistent storage | Don’t have to re-enter data | See Lecture 15 for an object-oriented strategy to create the file format
LOAD | 13 | 3 |  | 8 | 3 | Finished in Sprint 3 | All | Load data for a school from persistent storage | Don’t have to re-enter data | Select file via a file chooser dialog
SAVEAS | 14 | 3 |  | 8 | 3 | Finished in Sprint 3 | Administrator | Save data to a different filename | Create backups or baselines for new schools | Select filename via a file chooser dialog
TOOLBAR | 15 | 3 |  | 5 | 3 | Finished in Sprint 3 | All | Use the major features via a toolbar | Point and click | Suggest using the Nim game’s toolbar as a baseline
ABOUT | 16 | 3 |  | 1 | 3 | Finished in Sprint 3 | Administrator | Display an About dialog with creator and version | Quickly determine which version is installed | Use Gtk::AboutDialog
COURSE | 17 | 4 |  | 21
SEMESTER | 18 | 4 |  | 8
SECTION | 19 | 4 |  | 5
20
21
22
SUBJECT | 23 | 5
TEACHER | 24 | 5 |  | 21
GRADE | 25 | 5 |  | 5
TRANSCRIPT | 26 | 5 |  | 8
ITERATORS | 27 | 5 |  | 8
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2021-03-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 10 | 3
Day 2 Left | 10 | 0
Day 3 Left | 3 | 7
Day 4 Left | 1 | 2
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 0 | 1
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 | PERSON |  | Code person.h | Completed Day 1
2 | PERSON |  | Code person.cpp | Completed Day 1
3 | PERSON |  | Test compile Person class | Completed Day 1
4 | STUDENT |  | Code student.h | Completed Day 3
5 | STUDENT |  | Code student.cpp | Completed Day 3
6 | STUDENT |  | Test compile Student class | Completed Day 3
7 | PARENT |  | Duplicate Student to Parent | Completed Day 3
8 | PARENT |  | Remove grade, update to_string() and full_info() | Completed Day 3
9 | PARENT |  | Test compile Parent class | Completed Day 3
10 | RELATE |  | Build with example code and verify | Completed Day 3
11 | CLI |  | (Bonus) Write CLI | Completed Day 4
12 | CLI |  | (Bonus) Test CLI | Completed Day 4
13 | CLI |  | (Bonus) Fix (work-around) vector reallocation bug | Completed Day 7
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2021-03-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 13 | 0
Day 2 Left | 7 | 6
Day 3 Left | 5 | 2
Day 4 Left | 5 | 0
Day 5 Left | 4 | 1
Day 6 Left | 3 | 1
Day 7 Left | 0 | 3
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WINDOW |  | Baseline main.cpp from nim | Completed Day 2
2 | WINDOW |  | Update Makefile for gtkmm | Completed Day 2
3 | WINDOW |  | Baseline Mainwin class from nim | Completed Day 2
4 | D_STUDENT |  | Baseline EntryDialog class from Lecture 14 | Completed Day 2
5 | WINDOW |  | Create menu for SMART in Mainwin class | Completed Day 2
6 | DISPLAY |  | Add display label, vectors, and show_data method | Completed Day 2
7 | D_STUDENT |  | Write on_new_student_click using EntryDialog | Completed Day 3
8 | D_PARENT |  | Write on_new_parent_click using EntryDialog | Completed Day 3
9 | D_RELATE |  | Write on_student_parent_click using EntryDialog | Completed Day 5
10 | WINDOW |  | Add Easter egg to support testing and demos | Completed Day 7
11 | WINDOW |  | Refactor: select, select_student, and select_parent methods | Completed Day 7
12 | WINDOW |  | Test and improve error handling | Completed Day 6
13 | WINDOW |  | Backport bug fixes from P07 | Completed Day 7
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2021-03-23 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 5
Day 1 Left | 5 | 0
Day 2 Left | 3 | 2
Day 3 Left | 3 | 0
Day 4 Left | 0 | 3
Day 5 Left | 0 | 0
Day 6 Left | -1 | 1
Day 7 Left | -1 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | Save |  | Save the smart file with .smart file extension as default | Completed Day 2
2 | Load |  | Load the smart file and create a a smart system from data from file | Completed Day 2
3 | SaveAs |  | Save as user choosed file extension | Completed Day 4
4 | Toolbar |  | Create a toolbar for quick access to different functionality | Completed Day 4
5 | About |  | Create a about window for license, credits and certification for the software | Completed Day 4
6 |  |  |  | Completed Day 6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-04-06 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-13
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2021-04-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84